## START HERE
Project Cost Management Model
Worksheet Legend |  |  | Cell Format Legend
BLACK | Instructions/Legend |  |  | can change cell value (input)
GREEN | Control |  |  | make a selection (list)
BLUE | Editable Sheets |  |  | do not change cell value (calculation)
GREY | Calculation worksheets
NOTE: This template is an example cost management tool and should be adapted according to the needs and processes of the lead agency.
Entering Data into the Model: INPUTS WORKSHEET
Enter all INPUTS & ASSUMPTIONS in the Inputs Worksheet.
Input cells are shaded YELLOW & the text will appear in blue.
All other cells are protected to ensure formulas are not altered.
Setting up Planned Costs: PLANNED WORKSHEET
Planned costs need to be accurately extrapolated across the delivery period based on estimated utilisation for the Project Team and deliverable dates for Advisors. The planned costs are agreed with the Agency and are populated from the Schedule.
Data Input: INVOICES
The Invoices worksheet drives the model. Invoices are recorded by individual, not by company. If a company has more than one resource, the invoice will need to be split across the resources. The ACTUALS worksheet is dependent on the data entered in the Invoices spreadsheet.
NOTE: You can only record one entry per month. If you received two invoices in the same month, they will need to be added together and the notes recorded in the notes section.
DASHBOARD WORKSHEET
The Dashboard summaries the data in the workbook and generates graphs that are utilised in reports.
The summaries include:
· Cumulative budget v actual costs and cost to complete displayed in a graph
· Monthly budget v actual cost for the current month (Use the drop down list to switch between months)
· Cumulative budget v actual cost displayed in table and graph form
· Contract budget v actual cost displayed in table and graph form

## DASHBOARD
PROJECT NAME: |  | PROJECT NAME
Cumulative Budget v Actual
TOTAL
| Difference |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Cumulative Expenditure (Budget) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Forecast (Cost to complete) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Expenditure (Actual) | #N/A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Project Team Costs - Monthly Budget vs Actual |  |  |  |  | Last Updated:
2018-12-31
PROJECT TEAM
|  |  |  | Budget |  | Actual |  | Over/Under
Business Case Management | 0 |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
External Resources
Advisor 1 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 2 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 3 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 4 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 5 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 6 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 7 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 8 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 9 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 10 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 11 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE1 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE2 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE3 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE4 | 0 |  |  | #N/A |  | #N/A |  | #N/A
|  |  |  | #N/A |  | #N/A |  | #N/A
Project Team Costs - Cumulative Budget vs Actual | [6 empty] | CHANGE
2018-12-31
PROJECT TEAM
|  |  |  | Budget |  | Actual |  | Over/Under
Business Case Management | 0 |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
0 | #N/A |  |  | #N/A |  | #N/A |  | #N/A
External Resources
Advisor 1 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 2 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 3 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 4 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 5 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 6 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 7 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 8 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 9 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 10 | 0 |  |  | #N/A |  | #N/A |  | #N/A
Advisor 11 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE1 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE2 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE3 | 0 |  |  | #N/A |  | #N/A |  | #N/A
SPARE4 | 0 |  |  | #N/A |  | #N/A |  | #N/A
|  |  |  | #N/A |  | #N/A |  | #N/A
Contracts - Budget vs Actual (by team member) | [5 empty] | TODAY | 2025-12-23
2025-12-31
PROJECT TEAM
|  |  | Contract End | Contract Value |  | Actual Spend | % spend | Balance Remaining
Business Case Management | 0 |  | 0 | 0 |  | #N/A | #N/A | #N/A
0 | #N/A |  | #N/A | #N/A |  | #N/A | #N/A | #N/A
0 | #N/A |  | #N/A |  |  | #N/A |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A
0 | #N/A |  | #N/A |  |  | #N/A
External Resources
Advisor 1 | 0 |  | 0 | 0 |  | #N/A | #N/A | #N/A
Advisor 2 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
Advisor 3 | 0 |  | 0 | 0 |  | #N/A | #N/A | #N/A
Advisor 4 | 0 |  | 0 | 0 |  | #N/A | #N/A | #N/A
Advisor 5 | 0 |  | 0 | 0 |  | #N/A | #N/A | #N/A
Advisor 6 | 0 |  | 0 | 0 |  | #N/A | #N/A | #N/A
Advisor 7 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
Advisor 8 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
Advisor 9 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
Advisor 10 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
Advisor 11 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
SPARE1 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
SPARE2 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
SPARE3 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
SPARE4 | 0 |  | 0 | 0 |  | #N/A |  | #N/A
|  |  |  | #N/A | 0 | #N/A |  | #N/A

## INPUTS
PROJECT NAME: |  |  | PROJECT NAME
Todays date |  |  | 2025-12-23
INITATION
Dates
Start Year
Start Month
|  | Start Date | [8 empty] | #N/A
Project budget
Approved budget (including contingency and variations)
|  | Contract Budget | [8 empty] | 0
|  | Contingency | [8 empty] | 0
|  | Total budget (including variations & Contingency) | [8 empty] | 0
Internal Resources (ex GST) | [5 empty] | CONTRACT RATES
| Project Leadership Team |  | Resource | Resource Category | Company | Hrly rate | Hrs | Capped | % | CONTRACT BUDGET | APPROVED BUDGET | Contract Start | Contract End
|  | Business Case Management |  | Internal
[10 empty] | 0 | 0
External Service Providers (ex. GST)
Contract Data
Project Resourcing |  |  |  | Contract Value (ex GST) | Approved Budget (ex GST) | Contact Name |  |  |  | Contact Email | Company | Contract Start | Contract End
Advisor 1
Advisor 2
Advisor 3
Advisor 4
Advisor 5
Advisor 6
Advisor 7
Advisor 8
Advisor 9
Advisor 10
Advisor 11
SPARE1
SPARE2
SPARE3
SPARE4
INSERT LINE ABOVE
|  |  |  | 0 | 0
Variations
1
2
3
4
5
Contingency (ex GST)
| Contingency (approx 10%) | [9 empty] | 0
Note on P13: Nova Mason:Insert approved value from funding schedule PLUS any contract variations

## HEAD CONTRACT
Paste snippet of approved funding agreement from engagement letter with agency (if applicable)

## CONTRACT VARIATIONS
Vendor
Contract Number
Original Contract Value
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
0
Contract Number
0
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
0
Contract Number
0
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0
Vendor
Contract Number
Original Contract Value
0
Variation Number | Variation Date | Reason for Variation | Value (exc. GST) | GST | Total (inc. GST) | New Contract Value (exc. GST )
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 0

## FORECAST-UPDATE
PROJECT NAME: |  | PROJECT NAME
Monthly Project Cashflow (Planned)
Modelled Period |  | No |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Date |  | mm-yy |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Year |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Working Days in Period |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
In Range |  | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reforecast |  |  | #N/A
Project Leadership Team |  | Approved rate | Total
Business Case Management | Business Case Management | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
External Advisors
Advisor 1 | Advisor 1 | 0 | 0
Advisor 2 | Advisor 2 | 0 | 0
Advisor 3 | Advisor 3 | 0 | 0
Advisor 4 | Advisor 4 | 0 | 0
Advisor 5 | Advisor 5 | 0 | 0
Advisor 6 | Advisor 6 | 0 | 0
Advisor 7 | Advisor 7 | 0 | 0
Advisor 8 | Advisor 8 | 0 | 0
Advisor 9 | Advisor 9 | 0
Advisor 10 | Advisor 10 | 0
Advisor 11 | Advisor 11 | 0
SPARE1 | SPARE1 | 0
SPARE2 | SPARE2 | 0
SPARE3 | SPARE3 | 0
SPARE4 | SPARE4 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CUMULATIVE TOTAL (ex Contingency) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BUDGET
PROJECT NAME: |  | PROJECT NAME
Monthly Project Cashflow (Planned)
Modelled Period |  | No |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Date |  | mm-yy |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Year |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Working Days in Period |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
In Range |  | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Leadership Team |  | Approved rate | Total
Business Case Management | Business Case Management | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 1280 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
External Advisors
Advisor 1 | Advisor 1 | 0 | 0
Advisor 2 | Advisor 2 | 0 | 0
Advisor 3 | Advisor 3 | 0 | 0
Advisor 4 | Advisor 4 | 0 | 0
Advisor 5 | Advisor 5 | 0 | 0
Advisor 6 | Advisor 6 | 0 | 0
Advisor 7 | Advisor 7 | 0 | 0
Advisor 8 | Advisor 8 | 0
Advisor 9 | Advisor 9 | 0
Advisor 10 | Advisor 10 | 0
Advisor 11 | Advisor 11 | 0
SPARE1 | SPARE1 | 0
SPARE2 | SPARE2 | 0
SPARE3 | SPARE3 | 0
SPARE4 | SPARE4 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CUMULATIVE TOTAL (ex Contingency) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAST EXERPT FROM APPROVED FUNDING LETTER

## INVOICES
PROJECT NAME: |  | PROJECT NAME
Invoice Details
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Business Case Management | [5 empty] | Invoice Received | For The Month of… | Invoice Date | Value (ex GST) | GST | Total |  |  | Invoice Notes
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
Business Case Management31 | 0 | 0 |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  | Yes | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
0 | [6 empty] | For The Month of… |  |  | GST | Total
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
031 | #N/A | #N/A |  |  |  |  | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 1 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 2 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 3 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 4 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 5 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 531 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 6 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  |  | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 631 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 7 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 731 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 73131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 8 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 831 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 9 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 931 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 10 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1031 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
Advisor 11 | [6 empty] | For The Month of… |  |  | GST | Total
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
Advisor 1131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
SPARE1 | [6 empty] | For The Month of… |  |  | GST | Total
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE131 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
SPARE2 | [6 empty] | For The Month of… |  |  | GST | Total
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE231 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
SPARE3 | [6 empty] | For The Month of… |  |  | GST | Total
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE331 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
SPARE4 | [6 empty] | For The Month of… |  |  | GST | Total
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
SPARE431 | 0 | [5 empty] | 1900-01-30 |  |  | 0 | 0
TOTAL INVOICES | [8 empty] | 0 | 0 | 0
TOTAL INVOICED | [8 empty] | 0 | 0 | 0

## RECOVERY
AGENCY RECOVERY INVOICE OVERVIEW
0
INVOICE NO | CUSTOMER | MONTH | EXC GST | GST | INC GST
IN0000---
IN0000---
IN0000---
IN0000---
IN0000---
IN0000---
IN0000---
IN0000---
IN0000---
IN0000---
|  | SUB-TOTAL | 0 | 0 | 0
|  | Agreed Funding | 0 | 0 | 0
|  | Balance Remaining | 0 | 0 | 0

## FORECAST
PROJECT NAME: |  | PROJECT NAME
Monthly Project Cashflow (Planned)
Modelled Period |  | No |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Date |  | mm-yy |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Year |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Working Days in Period |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
In Range |  | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Leadership Team |  | Approved rate | Total
Business Case Management | Business Case Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
External Advisors
Advisor 1 | Advisor 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 2 | Advisor 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 3 | Advisor 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 4 | Advisor 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 5 | Advisor 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 6 | Advisor 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 7 | Advisor 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 8 | Advisor 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 9 | Advisor 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 10 | Advisor 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advisor 11 | Advisor 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPARE1 | SPARE1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPARE2 | SPARE2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPARE3 | SPARE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPARE4 | SPARE4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CUMULATIVE TOTAL (ex Contingency) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ACTUAL
PROJECT NAME: |  | PROJECT NAME
Monthly Project Cashflow (Actual)
Modelled Period |  | No |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Date |  | mm-yy |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Year |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Working Days in Period |  | No |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
In Range |  | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Leadership Team |  | Approved rate | Total
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Business Case Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
External Advisors
#N/A | Advisor 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | Advisor 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | SPARE1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | SPARE2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | SPARE3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | SPARE4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CUMULATIVE TOTAL (ex Contingency) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DATA (hidden)
Cumulative Planned vs Actual |  |  | Last Updated: | 2025-12-23
2025-12-31
Modelled Period |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Date |  | mm-yy |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Year |  | No |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Working Days in Period |  | No |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
In Range |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BUDGET by month
PROJECT TEAM
| Business Case Management |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 6 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 7 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 8 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 9 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 10 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 11 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTUAL by month
PROJECT TEAM
| Business Case Management |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 6 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 7 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 8 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 9 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 10 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advisor 11 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE3 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SPARE4 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## VALIDATION (hidden)
Lists
Months in the Year
| January |  | 1
| February |  | 2
| March |  | 3
| April |  | 4
| May |  | 5
| June |  | 6
| July |  | 7
| August |  | 8
| September |  | 9
| October |  | 10
| November |  | 11
| December |  | 12
Billing Status
Accrual
Actual
Invoice Status
Received
Not Received
No Charges in the Month
Public Holidays |  | Dates
| Christmas day | 2017-12-25
| Boxing day | 2017-12-26
| Christmas holiday1 | 2017-12-27
| Christmas holiday2 | 2017-12-28
| Christmas holiday3 | 2017-12-29
| New Years Day | 2018-01-01
| Australia Day | 2018-01-26
| Good Friday | 2018-03-30
| Easter Monday | 2018-04-02
| Anzac Day | 2018-04-25
| Labour Day | 2018-04-07
| EKKA Day | 2018-08-15
| Queens Birthday | 2018-10-01
| Christmas Day | 2018-12-25
| Boxing day | 2018-12-26
| Christmas holiday1 | 2018-12-27
| Christmas holiday2 | 2018-12-28
| Christmas holiday3 | 2018-12-29
| New Years Day | 2019-01-01
| Australia Day | 2019-01-26
INSERT LINE ABOVE
Resource Category
| 1 | Internal
| 2 | External
| 3 | SpecialAdvisor
| 4 | Overhead
| 5 | Contingency
| 6 | Other Agency
| 7 | Other Agency-Advisor