## How to use this template
Detailed Business Case (DBC) Alignment Review Template directions
1 | Read the Purpose and Process tab
2 | Complete kick-off activities described in the Purpose and Process tab
3 | To complete your initial review, populate columns B to C n the Alignment Review tab
4 | To complete your final review, populate columns D to E in the Alignment Review tab. Note any changes that have occurred since your initial review. You can copy directly from your initial review where the content still applies. Document how any misalignment or tailoring were agreed to. PSC should be briefed on significant misalignments for endorsement and should be noted all the way through.
5 | Depending on the agreed arrangements, Department of State Development, Infrastructure and Planning (DSDIP) may confirm, check or review your final review. Share the final review with DSDIP if it has been agreed. They will provide feedback in columns F and G. You should update your review as required. If it was determined that a DSDIP confirm, check or review is not required, disregard this step and delete columns F and G.
6 | The final Alignment Review Report forms part of the Assurance Report. It should only include points where the proposal does not align with the BCDF. Where there are points of misalignment in your final review, copy the cells from columns D and E in the Alignment Review tab into columns B and C in the Final Alignment Review Report tab. Delete any rows in the Final Alignment Review tab that are not populated (i.e. that align with the BCDF). This should form a succinct report that you can copy directly into the Assurance Report.

## Purpose and Process
DBC Alignment Review purpose and process
Purpose
The Business Case Development Framework (BCDF) provides guidance on the preferred content for a Stage 3: Detailed Business Case. The Infrastructure Proposal Assurance Framework sets out the requirement to complete a BCDF alignment review. The review confirms a detailed business case has considered the key aspects outlined in the BCDF.
The purpose of the review is to:
1. Guide and assist project teams to develop proposals that align with the intent of the BCDF and are transparent, robust, coherent and form a strong argument that supports the conclusions and recommendations
2. Provide an opportunity to build proposal development capability regarding the BCDF with proposal teams and (directly or indirectly) advisors
3. Document and report the findings, recommendations and actions (planned or taken) arising from the assurance activities detailed in the Assurance Plan for the proposal in order to provide confidence to the key decision-makers (i.e. project sponsors, Project Steering Committee, Investment and Assurance Committees, Boards and/or ICC and CBRC) that the business case aligns to the expectations of the responsible agency and the requirements of government's Infrastructure Proposal Development Policy.
The review is to be undertaken against the documented elements of the BDCF, comparing the detailed business case against what is outlined in the BCDF guidance. Further detail of what the review should consider is set out in the checklist and process section below. Note the BCDF CBA Guide also includes checklists which need to be completed for the economic analysis and in the advisor's report. The review does not need to include a detailed check of the analysis undertaken for the DBC, or an editorial/writing style review of DBC sections. The review focuses on confirming that the business case sections reflect the intent, guidance and process in the relevant components of the BCDF, and/or explain the rationale and consequences for any alternate approach. It should test alignment with the intent of each section and subsection, not just whether the section and subsection exist. This may require multiple reviews, which is reflected in the need for a three-stage process. Further detail on this is in the Process section below.
Process
The BCDF alignment review is to be completed iteratively through the development of the proposal sections and before the sections are finalised. Once completed, the Alignment Review will form part of the Assurance Report. The review is undertaken by the agency or other entity responsible for leading the development of the detailed business case (the proposal team). The reviewer will complete this table for the detailed business case and will provide it to the proposal’s Business Case Director and a member of DSDIP’s Infrastructure Portfolio and Advisory (DSDIP representative) who has been engaged throughout the duration of the proposal’s detailed business case.
The BCDF alignment review provides an opportunity for improvement during the development of the proposal rather than just a scorecard at the end. To enable this, the Alignment Review process has the following stages:
1. Assurance Kick-off: As part of the establishment of all assurance requirements for the proposal, DSDIP will engage with your proposal team to:
Explain the alignment review purpose and process
Discuss tailoring requirements, if any, that might apply to your proposal
Agree on the timing of key activities, including the initial and final alignment reviews conducted by your proposal team, and the degree of DSDIP involvement. Timing for these activities will be considered within the proposal schedule and documented in the Assurance Plan for the proposal
Share lessons learned from previous proposals
2. Initial draft content review: the proposal team, working with technical advisors, will ensure all content required by the BCDF is covered, the assessment methodology is sound, etc. A BCDF alignment review involves:
Reviewing each section to ensure the content aligns to BCDF expectations and intent. Where it does not, describe the reasoning and consequences
Reviewing the content of the section to ensure it is appropriate, relevant, evidence-based, objective and transparent
Reviewing the entire document to ensure the narrative is clear and argument flows, is consistent and coherent and uses objective language.
Documenting alignment review findings in the Alignment Review template, which is progressively updated as the proposal is developed and through discussions between the proposal team and DSDIP.
3. Final Review: Prior to the Gateway Review and when the proposal's sections are close to finalisation, the proposal team will complete a final Alignment Review. DSDIP will conduct a final check of the review outcomes and provide feedback to the proposal team.
DSDIP and the proposal team are to agree on the timing of the kick-off and reviews, and are to allow a minimum of one week for DSDIP to complete a final check. Should there be any questions, the agency or other entity responsible for developing the proposal are welcome to contact their nominated DSDIP representative at any time during the development of the Alignment Review.
Reporting
The outcome of the final review is to be included in the Assurance Report and any other assurance requirements, noting the date of completion. The Assurance Report is to be presented by the proposal team to the key decision makers for consideration and endorsement.

## DBC Alignment Review
DBC Alignment Review
| Proposal Team: Initial Review |  | Proposal Team: Final Review |  | DSDIP: Final Check
Business Case Key Content | Alignment with the BCDF (Yes/No) | If not aligned to the BCDF, describe the reasoning and consequences (note: variations to the BCDF should be reported in the Assurance Section of the DBC) | Alignment with the BCDF (Yes/No) | If not aligned to the BCDF, describe the reasoning and consequences (note: variations to the BCDF should be reported in the Assurance Chapter of the DBC) | Comment | Action
SECTION A – PROPOSAL CONTEXT
Executive Summary, including
Recommendations for decision makers
1. Proposal background (A1)
1.1 Proposal context
1.2 History of the proposal
2. Governance and Assurance (A2)
2.1 Proposal owner
2.2 Overall approach to business case
2.3 Steering committee
2.4 Working group/s
2.5 Project team roles and responsibilities
Assurance
2.6 Approach
2.7 Assurance activities
3. Service Need (A3)
3.1 Service need
3.2 Stakeholders and engagement
3.3 Current state
3.4 Benefits sought
3.5 Options analysis
3.6 Recommended option/s (Reference project/s)
4. Strategic Considerations (A4)
4.1 Strategic alignment
4.2 Policy issues
SECTION B – CONSIDERATIONS AND ANALYSIS
5. Risk (B1)
5.1 Overall approach to risk
5.2 Risk framework
5.3 Outcomes
6. Base Case (B2)
6.1 Approach
6.2 Base case
6.3 Outcomes
7. Reference Project/s (B3)
7.1 Approach
7.2 Objectives, outcomes and benefits
7.3 Scope
7.4 Activities
7.5 Reference design
8. Legal and Regulatory Considerations (B4)
8.1 Legislative issues
8.2 Regulatory issues
8.3 Approvals
8.4 Other legal matters
9. Public Interest Consideration (B5)
9.1 Approach
9.2 Community consultation/stakeholder engagement
9.3 Impact on stakeholders
9.4 Public access and equity
9.5 Social licence status
9.6 Consumer rights
9.7 Safety and security
9.8 Privacy
10. Sustainability Assessment (B6)
10.1 Approach
10.2 Sustainability assessment results
11. Social Impact Evaluation (B7)
11.1 Approach
11.2 Social impact baseline
11.3 Evaluation
11.4 Impact summary
11.5 Impact of the project
11. 6 Negative impacts and their mitigations
11.7 Additional opportunities
11.8 Integration
12. Environmental Assessment (B8)
12.1 Approach
12.2 Identification of environmental impacts
12.3 Environmental impacts
13. Economic Analysis (B9)
13.1 Approach
13.2 Benefits
13.3 Costs
13.4 Cost benefit analysis results
13.5 Socio-economic narrative
13.6 Scenario and sensitivity analysis
13.7 Quality assurance review and results
Completed the checklist in the CBA guide
14. Financial Analysis (B10)
14.1 Approach
14.2 Financial analysis
14.3 Commercial analysis (if required)
14.4 Assurance review and results
14.5 Analysis summary
15. Affordability Analysis (B11)
15.1 Approach
15.2 Affordability assessment
16. Appraisal Summary Table (B12)
16.1 Summary of key consequences
SECTION C – DELIVERY
17. Market Considerations (C1)
17.1 Approach
17.2 Outcomes
18. Delivery Model Analysis (C2)
18.1 Approach
18.2 Outcomes
18.3 Private finance delivery model assessment
19. Public Sector Comparator (C3)
19.1 Approach
19.2 Public Sector Comparator Assessment
20. Implementation Plan (C4)
20.1 Governance
20.2 Project management plan
20.3 Procurement strategy and plan
20.4 Change management
20.5 Resource requirements
20.6 Benefits realisation
Conclusions
Outcomes of the analyses
Recommendations
Recommendations
Next steps
Health check C
References
Appendices
Relevant appendices may include:
Assurance Report (with Assurance Plan as attachment)
Benefits Register
Risk Register
Stakeholder Engagement Plan
Outcome: (choose one of the options below)
The BCDF alignment review has been completed; alignment to the Framework has been confirmed.
The BCDF alignment review has been completed; any significant variations against the Framework have been identified, agreed and documented.
BCDF Review completion date: (insert date)
Provided to DSDIP representative: (insert date)
[FOR DSDIP] DSDIP outcome: (chose one of the options below)
DSDIP alignment review check has been completed; alignment to the Framework has been confirmed.
DSDIP alignment review check has been completed; any significant variations against the Framework have been identified, agreed and documented.
DSDIP representative: (insert name and date)

## Final DBC Alignment Rvw Report
Final DBC Alignment Review Report
Note: This template is aligned to the Stage 3: Detailed Business Case Template (available as a Microsoft word document)
Business Case key content | Alignment with the BCDF (Yes/No) | If not aligned to the BCDF, describe the reasoning and consequences (note: variations to the BCDF should be reported in the Assurance Section of the DBC)
SECTION A – PROPOSAL CONTEXT
Executive Summary, including
Recommendations for decision makers
1. Proposal background (A1)
1.1 Proposal context
1.2 History of the proposal
2. Governance and Assurance (A2)
2.1 Proposal owner
2.2 Overall approach to business case
2.3 Steering committee
2.4 Working group/s
2.5 Project team roles and responsibilities
Assurance
2.6 Approach
2.7 Assurance activities
3. Service Need (A3)
3.1 Service need
3.2 Stakeholders and engagement
3.3 Current state
3.4 Benefits sought
3.5 Options analysis
3.6 Recommended option/s (Reference project/s)
4. Strategic Considerations (A4)
4.1 Strategic alignment
4.2 Policy issues
SECTION B – CONSIDERATIONS AND ANALYSIS
5. Risk (B1)
5.1 Overall approach to risk
5.2 Risk framework
5.3 Outcomes
6. Base Case (B2)
6.1 Approach
6.2 Base case
6.3 Outcomes
7. Reference Project/s (B3)
7.1 Approach
7.2 Objectives, outcomes and benefits
7.3 Scope
7.4 Activities
7.5 Reference design
8. Legal and Regulatory Considerations (B4)
8.1 Legislative issues
8.2 Regulatory issues
8.3 Approvals
8.4 Other legal matters
9. Public Interest Consideration (B5)
9.1 Approach
9.2 Community consultation/stakeholder engagement
9.3 Impact on stakeholders
9.4 Public access and equity
9.5 Social licence status
9.6 Consumer rights
9.7 Safety and security
9.8 Privacy
10. Sustainability Assessment (B6)
10.1 Approach
10.2 Sustainability assessment results
11. Social Impact Evaluation (B7)
11.1 Approach
11.2 Social impact baseline
11.3 Evaluation
11.4 Impact summary
11.5 Impact of the project
11. 6 Negative impacts and their mitigations
11.7 Additional opportunities
11.8 Integration
12. Environmental Assessment (B8)
12.1 Approach
12.2 Identification of environmental impacts
12.3 Environmental impacts
13. Economic Analysis (B9)
13.1 Approach
13.2 Benefits
13.3 Costs
13.4 Cost benefit analysis results
13.5 Socio-economic narrative
13.6 Scenario and sensitivity analysis
13.7 Quality assurance review and results
Completed the checklist in the CBA guide
14. Financial Analysis (B10)
14.1 Approach
14.2 Financial analysis
14.3 Commercial analysis (if required)
14.4 Assurance review and results
14.5 Analysis summary
15. Affordability Analysis (B11)
15.1 Approach
15.2 Affordability assessment
16. Appraisal Summary Table (B12)
16.1 Summary of key consequences
SECTION C – DELIVERY
17. Market Considerations (C1)
17.1 Approach
17.2 Outcomes
18. Delivery Model Analysis (C2)
18.1 Approach
18.2 Outcomes
18.3 Private finance delivery model assessment
19. Public Sector Comparator (C3)
19.1 Approach
19.2 Public Sector Comparator Assessment
20. Implementation Plan (C4)
20.1 Governance
20.2 Project management plan
20.3 Procurement strategy and plan
20.4 Change management
20.5 Resource requirements
20.6 Benefits realisation
Conclusions
Outcomes of the analyses
Recommendations
Recommendations
Next steps
Health check C
References
Appendices
Relevant appendices may include:
Assurance Report (with Assurance Plan as attachment)
Benefits Register
Risk Register
Stakeholder Engagement Plan
Outcome: (choose one of the options below)
The BCDF alignment review has been completed; alignment to the Framework has been confirmed.
The BCDF alignment review has been completed; any significant variations against the Framework have been identified, agreed and documented.
BCDF Review completion date: (insert date)
Provided to DSDIP representative: (insert date)
[FOR DSDI] DSDIP outcome: (chose one of the options below)
DSDIP alignment review check has been completed; alignment to the Framework has been confirmed.
DSDIP alignment review check has been completed; any significant variations against the Framework have been identified, agreed and documented.
DSDIP representative: (insert name and date)