## How to use this template
Options Analysis (OA) Alignment Review Template directions
1 | Read the Purpose and Process tab
2 | Complete kick-off activities described in the Purpose and Process tab
3 | To complete your initial review, populate columns B to C n the Alignment Review tab
4 | To complete your final review, populate columns D to E in the Alignment Review tab. Note any changes that have occurred since your initial review. You can copy directly from your initial review where the content still applies. Document how any misalignment or tailoring were agreed to. PSC should be briefed on significant misalignments for endorsement and should be noted all the way through.
5 | Depending on the agreed arrangements, the Department of State Development, Infrastructure and Planning (DSDIP) may confirm, check or review your final review. Share the final review with DSDIP if it has been agreed. They will provide feedback in columns F and G. You should update your review as required. If it was determined that a DSDIP confirm, check or review is not required, disregard this step and delete columns F and G.
6 | The final Alignment Review Report forms part of the Assurance Report. It should only include points where the proposal does not align with the BCDF. Where there are points of misalignment in your final review, copy the cells from columns D and E in the Alignment Review tab into columns B and C in the Final Alignment Review Report tab. Delete any rows in the Final Alignment Review tab that are not populated (i.e. that align with the BCDF). This should form a succinct report that you can copy directly into the Assurance Report.

## Purpose and Process
OA Alignment Review purpose and process
Purpose
The Business Case Development Framework (BCDF) provides guidance on the preferred content for a Stage 2: Options Analysis. The Infrastructure Proposal Assurance Framework sets out the requirement to complete a BCDF alignment review. The review confirms an OA has considered the key aspects outlined in the BCDF.
The purpose of the review is to:
1. Guide and assist project teams to develop proposals that align with the intent of the BCDF and are transparent, robust, coherent and form a strong argument that supports the conclusions and recommendations
2. Provide an opportunity to build proposal development capability regarding the BCDF with proposal teams and (directly or indirectly) advisors
3. Document and report the findings, recommendations and actions (planned or taken) arising from the assurance activities detailed in the Assurance Plan for the proposal in order to provide confidence to the key decision-makers (i.e. project sponsors, Project Steering Committee, Investment and Assurance Committees, Boards and/or ICC and CBRC) that the business case aligns to the expectations of the responsible agency and the requirements of government's Infrastructure Proposal Development Policy.
The review is to be undertaken against the documented elements of the BDCF, comparing the OA against what is outlined in the BCDF guidance. Further detail of what the review should consider is set out in the checklist and process section below. Note the BCDF CBA Guide also includes checklists which need to be completed for the economic analysis and in the advisor's report. The review does not need to include a detailed check of the analysis undertaken for the OA, or an editorial/writing style review of OA sections. The review focuses on confirming that the business case sections reflect the intent, guidance and process in the relevant components of the BCDF, and/or explain the rationale and consequences for any alternate approach. It should test alignment with the intent of each section and subsection, not just whether the section and subsection exist. This may require multiple reviews, which is reflected in the need for a three-stage process. Further detail on this is in the Process section below.
Process
The BCDF alignment review is to be completed iteratively through the development of the proposal sections and before the sections are finalised. Once completed, the Alignment Review will form part of the Assurance Report. The review is undertaken by the agency or other entity responsible for leading the development of the OA (the proposal team). The reviewer will complete this table for the OA and will provide it to the proposal’s Business Case Director and a member of DSDIP’s Infrastructure Portfolio and Advisory team (DSDIP representative) who has been engaged throughout the duration of the proposal’s OA.
The BCDF alignment review provides an opportunity for improvement during the development of the proposal rather than just a scorecard at the end. To enable this, the Alignment Review process has the following stages:
1. Assurance Kick-off: As part of the establishment of all assurance requirements for the proposal, DSDIP will engage with your proposal team to:
Explain the alignment review purpose and process
Discuss tailoring requirements, if any, that might apply to your proposal
Agree on the timing of key activities, including the initial and final alignment reviews conducted by your proposal team, and the degree of DSDIP involvement. Timing for these activities will be considered within the proposal schedule and documented in the Assurance Plan for the proposal
Share lessons learned from previous proposals
2. Initial draft content review: the proposal team, working with technical advisors, will ensure all content required by the BCDF is covered, the assessment methodology is sound, etc. A BCDF alignment review involves:
Reviewing each section to ensure the content aligns to BCDF expectations and intent. Where it does not, describe the reasoning and consequences
Reviewing the content of the section to ensure it is appropriate, relevant, evidence-based, objective and transparent
Reviewing the entire document to ensure the narrative is clear and argument flows, is consistent and coherent and uses objective language.
Documenting alignment review findings in the Alignment Review template, which is progressively updated as the proposal is developed and through discussions between the proposal team and DSDIP.
3. Final Review: Prior to the Gateway Review and when the proposal's sections are close to finalisation, the proposal team will complete a final Alignment Review. DSDIP will conduct a final check of the review outcomes and provide feedback to the proposal team.
DSDIP and the proposal team are to agree on the timing of the kick-off and reviews, and are to allow a minimum of one week for DSDIP to complete a final check. Should there be any questions, the agency or other entity responsible for developing the proposal are welcome to contact their nominated DSDIP representative at any time during the development of the Alignment Review.
Reporting
The outcome of the final review is to be included in the Assurance Report and any other assurance requirements, noting the date of completion. The Assurance Report is to be presented by the proposal team to the key decision makers for consideration and endorsement.

## OA Alignment Review
OA Alignment Review
| Proposal Team: Initial Review |  | Proposal Team: Final Review |  | DSDIP: Final Confirmation/Check/Review [select one]
Business Case key content | Alignment with the BCDF (Yes/No) | If not aligned to the BCDF, describe the reasoning and consequences (note: variations to the BCDF should be reported in the Assurance Section of the DBC) | Alignment with the BCDF (Yes/No) | If not aligned to the BCDF, describe the reasoning and consequences (note: variations to the BCDF should be reported in the Assurance Chapter of the DBC) | Comment | Action
SECTION A – PROPOSAL CONTEXT
Executive Summary, including
Recommendations for decision makers
1. Proposal background (A1)
1.1 Proposal context
1.2 Review of Stage 1: Strategic Assessment
2. Governance and Assurance (A2)
2.1 Proposal owner
2.2 Overall approach to business case
2.3 Steering committee
2.4 Working group/s
2.5 Project team roles and responsibilities
Assurance
2.6 Approach
2.7 Assurance activities
3. Service Need (A3)
3.1 Service need statement
3.2 Stakeholders and stakeholder engagement
3.3 Current state
3.4 Benefits targeted
4. Base Case (A4)
4.1 Approach
4.2 Base case
Health Check A
SECTION B – OPTIONS LONGLIST TO SHORTLIST
5. Options longlist (B1)
5.1 Options longlist
6. Options longlist to shortlist (B2)
6.1 Approach
6.2 Supporting analysis
6.3 Filtering analysis
Health Check B
SECTION C – OPTIONS ANALYSIS CONSIDERATIONS
Approach
7. Social Impact Evaluation (C1)
7.1 Approach
7.2 Social impact baseline
7.3 Evaluation
7.4 Impact summary
7.5 Additional opportunities
7.6 Integration
8. Environmental Assessment (C2)
8.1 Approach
8.2 Identification of environmental impacts
8.3 Environmental assessment
9. Sustainability Assessment (C3)
9.1 Approach
9.2 Sustainability assessment results
10. Economic Analysis (C4)
10.1 Approach
10.2 Economic benefits
10.3 Economic costs
10.4 Cost benefit analysis results and socio-economic narrative
10.5 Sensitivity and scenario analysis
10.6 Quality assurance review and results
11. Financial analysis (C5)
11.1 Approach
11.2 Financial analysis
11.3 Building information modelling
11.4 Commercial analysis
11.5 Analysis summary
12. Affordability analysis (C6)
12.1 Approach
12.2 Affordability assessment
Health Check C1
13. Options analysis (C7)
13.1 Approach
13.2 Analysis summary
13.3 Preferred option/s
Health Check C2
SECTION D – PREFERRED OPTION/S IMPLEMENTATION CONSIDERATIONS
14. Market considerations (D1)
14.1 Approach
14.2 Outcomes
15. Delivery model analysis (D2)
15.1 Approach
15.2 Traditional delivery model assessment
15.3 PPP delivery model assessment
16. Next steps (D3)
16.1 Stage 3: Detailed business case plan
16.2 Communication plan
17. Conclusions
17.1 Outcome of the analyses
18. Recommendations
18.1 Viable option/s
18.2 Recommended actions
Health Check D
References
Appendix may include:
Appendix 1: Benefits register
Appendix 2: Risk register
Appendix 3: Stakeholder engagement plan
Appendix 4: Multi-criteria analysis
Outcome: (choose one of the options below)
The BCDF alignment review has been completed; alignment to the Framework has been confirmed.
The BCDF alignment review has been completed; any significant variations against the Framework have been identified, agreed and documented.
BCDF Review completion date: (insert date)
Provided to DSDIP representative: (insert date)
[FOR DSDIP] DSDIP outcome: (chose one of the options below)
DSDIP alignment review check has been completed; alignment to the Framework has been confirmed.
DSDIP alignment review check has been completed; any significant variations against the Framework have been identified, agreed and documented.
DSDIP representative: (insert name and date)

## OA Final Alignment Rvw Report
OA Final Alignment Review Report
OA Final Alignment Review Report
Business Case key content | Alignment with the BCDF (Yes/No) | If not aligned to the BCDF, describe the reasoning and consequences (note: variations to the BCDF should be reported in the Assurance Section of the DBC)
SECTION A – PROPOSAL CONTEXT
Executive Summary, including
Recommendations for decision makers
1. Proposal background (A1)
1.1 Proposal context
1.2 Review of Stage 1: Strategic Assessment
2. Governance and Assurance (A2)
2.1 Proposal owner
2.2 Overall approach to business case
2.3 Steering committee
2.4 Working group/s
2.5 Project team roles and responsibilities
Assurance
2.6 Approach
2.7 Assurance activities
3. Service Need (A3)
3.1 Service need statement
3.2 Stakeholders and stakeholder engagement
3.3 Current state
3.4 Benefits targeted
4. Base Case (A4)
4.1 Approach
4.2 Base case
Health Check A
SECTION B – OPTIONS LONGLIST TO SHORTLIST
5. Options longlist (B1)
5.1 Options longlist
6. Options longlist to shortlist (B2)
6.1 Approach
6.2 Supporting analysis
6.3 Filtering analysis
Health Check B
SECTION C – OPTIONS ANALYSIS CONSIDERATIONS
Approach
7. Social Impact Evaluation (C1)
7.1 Approach
7.2 Social impact baseline
7.3 Evaluation
7.4 Impact summary
7.5 Additional opportunities
7.6 Integration
8. Environmental Assessment (C2)
8.1 Approach
8.2 Identification of environmental impacts
8.3 Environmental assessment
9. Sustainability Assessment (C3)
9.1 Approach
9.2 Sustainability assessment results
10. Economic Analysis (C4)
10.1 Approach
10.2 Economic benefits
10.3 Economic costs
10.4 Cost benefit analysis results and socio-economic narrative
10.5 Sensitivity and scenario analysis
10.6 Quality assurance review and results
11. Financial analysis (C5)
11.1 Approach
11.2 Financial analysis
11.3 Building information modelling
11.4 Commercial analysis
11.5 Analysis summary
12. Affordability analysis (C6)
12.1 Approach
12.2 Affordability assessment
Health Check C1
13. Options analysis (C7)
13.1 Approach
13.2 Analysis summary
13.3 Preferred option/s
Health Check C2
SECTION D – PREFERRED OPTION/S IMPLEMENTATION CONSIDERATIONS
14. Market considerations (D1)
14.1 Approach
14.2 Outcomes
15. Delivery model analysis (D2)
15.1 Approach
15.2 Traditional delivery model assessment
15.3 PPP delivery model assessment
16. Next steps (D3)
16.1 Stage 3: Detailed business case plan
16.2 Communication plan
17. Conclusions
17.1 Outcome of the analyses
18. Recommendations
18.1 Viable option/s
18.2 Recommended actions
Health Check D
References
Appendix may include:
Appendix 1: Benefits register
Appendix 2: Risk register
Appendix 3: Stakeholder engagement plan
Appendix 4: Multi-criteria analysis
Outcome: (choose one of the options below)
The BCDF alignment review has been completed; alignment to the Framework has been confirmed.
The BCDF alignment review has been completed; any significant variations against the Framework have been identified, agreed and documented.
BCDF Review completion date: (insert date)
Provided to DSDIP representative: (insert date)
[FOR DSDIP] DSDIP outcome: (chose one of the options below)
DSDIP alignment review check has been completed; alignment to the Framework has been confirmed.
DSDIP alignment review check has been completed; any significant variations against the Framework have been identified, agreed and documented.
DSDIP representative: (insert name and date)