<<Proposal Name – Options Analysis/ Detailed Business Case>>Infrastructure Proposal Assurance Plan

<<MONTH YEAR>>

The Department of State Development, Infrastructure and Planning connects industries, businesses, communities and government (at all levels) to leverage regions’ strengths to generate sustainable and enduring economic growth that supports well-planned, inclusive and resilient communities.

      - Copyright

This publication is protected by the Copyright Act 1968.

      - Creative Commons licence

This work, except as identified below, is licensed by the Department of State Development, Infrastructure and Planning under a Creative Commons Attribution (CC BY) 4.0 Australia licence. To view a copy of this licence, visit creativecommons.org.au

You are free to copy, communicate and adapt this publication as long as you attribute it as follows:

© State of Queensland, the Department of State Development, Infrastructure and Planning, February 2025.

The licence does not apply to any branding, including the government coat of arms or government logos. Third party material that is not licensed under a Creative Commons licence is referenced within this document. All content not licensed under a Creative Commons licence is all rights reserved. Please contact the Department of State Development, Infrastructure and Planning/the copyright owner if you wish to use this material.

      - Translating and interpreting service

If you have difficulty understanding a document and need an interpreter, we provide access to a translating and interpreting service. You will not be charged for this service. To contact the Translating and Interpreting Service, telephone 131 450 and ask them to telephone the Department of State Development, Infrastructure and Planning on +61 7 3328 4811.

      - Disclaimer

      - The material published in this document is distributed by the Queensland Government as an information source only and is subject to change without notice.

      - The Queensland Government makes no statements, representations, or warranties about the accuracy, completeness or reliability of, and you should not rely on, any information contained in this document. You should make your own inquiries and obtain advice specific to your particular circumstances.

      - Despite our best efforts, the Queensland Government makes no warranties that the information in this online document is free of infection by computer viruses or other contamination.

      - To the extent permitted by law, the Queensland Government disclaims all responsibility and all liability (including without limitation, liability in negligence) for all expenses, losses (including direct and indirect losses), damages and costs you may incur as a result of the information in this document being inaccurate or incomplete in any way, and for any reason; or being subject to infection by computer viruses or other contamination.

      - Third-party websites

      - To the extent that there are any references or links to third-party websites contained in this document, you should be aware that third-party websites are not under our control and therefore we can make no representation concerning the content of these websites to you. The fact that we have referred you to these websites serve is not an endorsement by the State of Queensland of any of these websites.

      - References to third-party websites are provided only as a convenience to you. The Queensland Government does not warrant, guarantee or make any representation regarding the correctness, accuracy, reliability, currency, or any other aspect regarding characteristics or use of the information presented on third-party websites.

      - Where software is offered by a third-party website, you are advised that we may not have tested this software and therefore cannot make any representation regarding the quality, safety or suitability of any software found there. There are inherent dangers in the use of any software found on the Internet, and you are cautioned to make sure that you completely understand the risk before retrieving any software from the Internet.

      - Contact us

+61 7 3328 4811 or 13 QGOV (13 74 68)

@ info@dsdilgp.qld.gov.au

www.statedevelopment.qld.gov.au

PO Box 15009, City East, Queensland 4002

1 William Street, Brisbane 4000

Review and endorsement

| Action | Endorsed by | Name | Date |
| --- | --- | --- | --- |
| Developed | Project Director |  | Click or tap to enter a date. |
| Consulted | Infrastructure Portfolio and Advisory (IPA) |  | Click or tap to enter a date. |
| Consulted |  |  |  |
| Endorsed | Senior Responsible Officer (SRO) |  | Click or tap to enter a date. |
| Approved | Project Steering Committee (PSC) |  | Click or tap to enter a date. |
| Subsequent Approvals |  |  |  |
| Endorsed | SRO |  | Click or tap to enter a date. |
| Approved | PSC |  | Click or tap to enter a date. |

Document Control

| Document owner |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contact details |  |  |  |  |
| Version | Issue Date | Reason | Author | Approver |
| 1.0 |  |  |  |  |
| 2.0 |  |  |  |  |
| (Delete this box when draft is completed) Considerations – Infrastructure Portfolio and Advisory (IPA) is able to support agencies in the development of infrastructure proposals by providing best practice advice, templates and frameworks, as well as leveraging experience in proposal evaluation across various industry sectors and its relationships with and learnings from other infrastructure bodies. The level and extent of Department of State Development, Infrastructure and Planning (DSDIP) support should be discussed in the initial stages of developing the proposal and determined by IPA. Document Editing This template should be completed in conjunction with reading the Infrastructure Proposal Assurance Framework. Text marked in CYAN needs to be deleted Text marked in YELLOW needs to be reviewed and tailored to the proposal |  |  |  |  |  |

Contents

1.0	Introduction	7

1.1	Purpose	7

1.2	Infrastructure proposal objectives	8

1.3	Infrastructure proposal scope	8

1.4	Proposal overview	9

1.5	Proposal Governance	9

1.6	Proposal impact assessment	10

2.0	Assurance activities	13

2.1	Approach	13

2.2	Assurance program	15

2.3	Approach	18

# Introduction

Assurance constitutes a range of activities that are undertaken throughout the development of infrastructure proposals to ensure they are robust, transparent and provide a sound basis for government consideration and decision making.

Assurance planning was undertaken in line with the process for establishing assurance activities detailed in the Infrastructure Proposal Assurance Framework (Assurance Framework) illustrated in Figure 1.

Figure 1: Process for Establishing Assurance Activities

Assurance activities are integrated into the design of the infrastructure proposal development’s governance arrangements, project resourcing strategy, program, timeframe and budget. The links between assurance planning and project management planning is illustrated in Figure 2.

Figure 2: Assurance and project management planning

Any significant changes to the Assurance Plan arising from emerging or identified risks or material changes in key components to the business case are to be undertaken in consultation with the SRO and PSC accordingly.

- Throughout the document, a distinction is made between the following terms: Proposal being the ideas and options under development and to be put forward for government consideration and/or progression; and Project being the process and activities that will result in the development of the proposal.

## Purpose

This Assurance Plan documents the application of assurance activities for the <<Proposal Name Options Analysis (OA)/Detailed Business Case (DBC)>> ensuring the activities satisfy the fundamental assurance requirements set out in the Assurance Framework and providing confidence to decision-makers that:

- the infrastructure proposal responds to a clearly defined problem and/or opportunity

- business case analyses are fit for purpose

- data supporting the analyses are accurate, valid and reasonable

## Infrastructure proposal objectives

<<Remove EITHER, the following text for a DBC or the subsequent text for an OA.>>

The OA re-confirms and assess the long list of options from the Strategic Assessment and short-list preferred options.

The OA will involve developing stringent criteria and applying appropriate techniques to narrow the options. Any remaining options will be subjected to a rigorous evaluation of their potential viability using social-economic, environmental, financial and sustainability analysis and then ranked accordingly, taking into account the service need that they are designed to address.

The OA will result in an updated service need and identify preferred option/s supported by robust analysis.

OR

The DPC reconfirms the outcomes of the OA and provides a detailed analysis of the preferred option/s for investment decision-making and develop investment implementation plans.

The evaluation will involve a comprehensive assessment across all criteria (social, economic, environmental, financial and sustainability) using in-depth evaluation tools to develop conclusive evidence of investment viability (or otherwise) and certainty of expected outcomes.

The DBC process will result in a business case that provides clear recommendations for decision-makers, supported by comprehensive evidence.

## Infrastructure proposal scope

The OA/DBC will be prepared in accordance with the BCDF and Project Assessment Framework (PAF).

<< For some proposals, the Infrastructure Australia Assessment Framework will also apply and should be referenced here.>>

<<Remove EITHER, the following text for a DBC or the subsequent text for an OA.>>

The proposed OA scope includes key activities such as:

- verifying the analysis and outcomes from the previous stages in readiness for this stage, including a review of lessons learned

- reconfirming the service need and strategic context

- documenting how the proposed response contributes to government policy

- explaining the proposal scope, providing sufficient detail to allow decision-makers to understand how the service need will be addressed

- filtering the longlist of options to a shortlist

- confirming and assessing potential options, giving decisionmakers confidence that the most appropriate option/s should progress to the Stage 3: Detailed Business Case for more detailed analysis

- documenting the economic, social, environmental, financial and sustainable viability of shortlisted options to support selection of the preferred option/s

- recommending, where appropriate, option/s to be considered for detailed assessment in the Stage 3: Detailed Business Case

- considering whether the preferred option/s is suitable to be delivered as a Public Private Partnership (PPP) or should be progressed by a traditional delivery model

- performing assurance activities and incorporating all relevant feedback and recommendations.

OR

The proposed DBC scope includes key activities such as:

- conducting impact/benefits and impact assessment workshops incorporating effective stakeholder engagement

- re-evaluating the options analysis to confirm the reference project/s

- documenting and agreeing the base case

- undertaking a detailed, evidence-based analysis of the social, economic, financial and commercial impacts and the sustainability and environmental assessments, including scenario and sensitivity analysis

- completing:

  - cost/risk workshop

  - benefits workshop

  - market sounding workshop

  - delivery model assessment workshop

  - public sector comparator

  - implementation planning workshop

- performing assurance activities and incorporating all relevant feedback and recommendations.

## Proposal overview

<<Insert 2-3 paragraphs describing the context and a high-level description of the problem and /or opportunity that the Proposal will address / what it will achieve. Also state the strategic alignment of the proposal with department/ government objectives.>>

## Project Governance

Figure 3 shows the governance structure for the OA/DBC proposal. Full descriptions of the governance roles and responsibilities are detailed in the Business Case Management Plan (BCMP).

<<As the experience and expertise of project resources can be considered an assurance function, where possible, include names in the governance diagram or insert a table that documents the resources for the project.>>

Figure 3 Project Governance Structure

EDIT FIGURE AS REQUIRED

DBC
PROJECT TEAM

External Advisors

Responsible Minister

Assurance Processes: Peer and Gateway Reviews

Proposal Agency Executive

PROJECT STEERING COMMITTEE

Chair

Project Agency

IPA, DSDIP – if required

Proposal Owner Agency

Treasury

DPC

Proposal Agency Board
(if required)

Senior Responsible Owner

PWG

Proposal Agency Reps

DPC – if required

Treasury - if required

IPA, DSDIP – if required

Key Stakeholder Rep

Key Stakeholder Rep

Business Case Management Team

Business Case Director

## Proposal impact assessment

An assessment of the scale of high-risk impacts associated with the proposal and broader project was undertaken to inform the scope of assurance activities. The type and level of impacts identified have been used to build a program of appropriate assurance activities detailed in Section 3 – Assurance Program.

<<Provide a description of the impact assessment inputs, e.g. accessing lessons learned from similar projects, workshop/discussion with key stakeholders or other assessment process.>>

The proposal consequences, complexity and capability issues considered in the impact assessment and are presented in Table 1.

<<Edit Table 1 listing the key proposal and business case impacts/risks identified, including key areas of risk that may require assurance activities (such as technical inputs that would benefit from external peer review/s). Tailor the table to the considerations and outcomes specific to the project. Refer to Section 3.2 in the Infrastructure Proposal Assurance Framework for a list of potential impacts/risks. Using the matrix in Figure 4, provide a High, Medium or Low rating based on the likelihood and anticipated impact of the issue.>>

|  | Impact |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Low | Medium | High |
| Likelihood | High | Medium | High | High |
|  | Medium | Low | Medium | High |
|  | Low | Low | Low | Medium |

Figure 3: Impact assessment matrix

Table 1: Impact considerations and outcomes

| Considerations | Description of anticipated impacts | Rating |
| --- | --- | --- |
| Project / Proposal consequences |  |  |
| Stakeholder/user impact | e.g.: - The project will service 100,000 users annually. - Project has attracted significant interest in the community. |  |
| Economic outcomes |  |  |
| Financial |  |  |
| Reputational impact |  |  |
| Environmental |  |  |
| Other |  |  |
| Project / Proposal Complexity |  |  |
| Level of government priority |  |  |
| Multiple funding sources |  |  |
| Multiple stakeholders |  |  |
| Complexity of stakeholders, agency relationships |  |  |
| Complexity of solution |  |  |
| Design complexity |  |  |
| Delivery complexity |  |  |
| Bespoke solution |  |  |
| Interdependencies with other projects |  |  |
| Impact on operations during delivery |  |  |
| Level of organisational change once operational |  |  |
| Scrutiny – political, public, media |  |  |
| Election and/or political commitment |  |  |
| Agency / Project Team capability |  |  |
| Agency business case experience (includes Project Team and Advisors) |  |  |
| Project team (internal resources) experience in BCDF |  |  |
| Project team (advisors) experience in BCDF |  |  |
| Project Steering Committee members experience (includes business case development) |  |  |
| Agency delivery experience (includes construction) |  |  |

# Assurance activities

## Approach

After considering the impacts and ratings identified for the proposal and project, appropriate assurance activities were considered in relation to its scale and complexity across:

- Proposal governance: activities to ensure the proposal is completed on time, on budget and to the highest quality

- Quality assurance activities: internal and/or external assurance reviews or quality assessment undertaken throughout the development of the proposal to ensure the analyses are robust, transparent and defensible

- Close-out reviews: reviews to provide a level of assurance to project decision makers (e.g PSC and SRO) and government that the proposal outcomes are robust and transparent and ready for endorsement.

As explained in the Assurance Framework, assurance activities take place throughout the development of the proposal.

<<Transfer high (and relevant medium) rated impacts from Table 1 to Table 2 and document proposed assurance activities to respond to that high-risk impact.>> Refer to Section 3.3 in the Infrastructure Proposal Assurance Framework for examples of assurance activities.>>

Table 2: Assurance activities

| Description of potential impact | Assurance activity/s |
| --- | --- |

## Assurance program

The assurance program outlined in Table 3 provides a chronological view of assurance activities across the proposal development process.

<<Transfer assurance activities from Table 2 to Table 3 and allocate approximate timing and responsibility.>>

<<Re-order to establish where the activities fit within the program>>

<<Provide indicative dates for control points>>

<<Insert a table or Gantt chart showing the high-level schedule of business case development, assurance program and control points.>>

Table 3: Assurance Program

| Phase | Assurance activity | Description | Timing | Responsibility | Indicative cost |
| --- | --- | --- | --- | --- | --- |
| Preparatory work | Lessons learned review | e.g. Awareness of issues arising from previous business investigations or similar infrastructure proposals |  |  |  |
|  | Governance | e.g. DSDIP, DPC, QT review/participate in proposed governance arrangements Development of Terms of Reference |  |  |  |
|  | Key document development | e.g. Central agency (QT, DPC, DSDIP) review of key documents e.g. Terms of Reference, BC Management Plan, Assurance Plan |  |  |  |
|  | Additional content here |  |  |  |  |
| Proposal development | Peer reviews | e.g. Note specific peer reviews to be undertaken e.g. demand, design, engineering, economics, financial, environmental and sustainability |  |  |  |
|  | SME reviews | e.g. Reviews undertaken with either internal or other agency staff with specific expertise/knowledge |  |  |  |
|  | Community engagement | e.g. Community input into design and/or delivery |  |  |  |
|  | BCDF / PAF review | e.g. Check of alignment of the proposal with PAF and BCDF requirements (and the requirements of the Infrastructure Australia Assessment Framework, if applicable). |  |  |  |
|  | Gateway Review | e.g. A Gateway Review will be undertaken by an independent team arranged through the Queensland Treasury’s Gateway Unit. The objective of a Gate 2 Gateway Review is to ensure the project remains viable and can deliver its intended benefits |  |  |  |
|  | Additional content here |  |  |  |  |
| Close | Assurance | e.g. Check Infrastructure Proposal Assurance Plan has been executed appropriately including findings documented and communicated. |  |  |  |
|  | Lessons learned | e.g. Conduct lessons learned review |  |  |  |

## Approach

The Assurance Plan is endorsed by the SRO and approved by the Project Steering Committee (PSC) and will form the basis for ongoing reporting to the PSC on assurance activities.

The Assurance Plan forms the basis for ongoing reporting to the PSC on assurance activities. An example of a PSC assurance report (interim) is provided in the Assurance Framework.

In addition to regular reporting to the PSC on the progress of assurance activities, an Infrastructure Proposal Assurance Report (Assurance Report) must be prepared. The Assurance Report is prepared prior to completion of the proposal and forms part of the Appendices. It provides a summary of the outcomes of all Assurance Plan activities (including how recommendations from peer reviews and Gateway Reviews have been dealt with in the finalisation of the proposal) and enables owner agency to demonstrate how the proposal was developed in alignment with the Assurance Plan.

An Assurance Report template is available in the Infrastructure Proposal Development Toolkit.